## excel(4)
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 19.8 | 8.66 | 16
Planned Time | 0.22778 |  | 1899-12-31 09:44
Actual Tiempo |  | 0.33194 | 1899-12-31 12:01
CPI (Cost-Performance Index) |  |  | 0.94
% Reuse | 0% | 0% | 4.76%
% New Reusable | 33.3% | 26.1% | 3.12%
Test Defects/KLOC or equivalent | 11.8 | 0 | 10.4
Total Defects/KLOC or equivalent | 35.5 | 43.5 | 36.5
Yield % | 61.1% | 100% | 66.7%
Code Review Rate | 1332 | 218 | 785
% Appraisal COQ | 3.27% | 8.37% | 4.4%
% Failure COQ | 13.9% | 13.8% | 13.9%
COQ A/F Ratio | 0.24 | 0.61 | 0.32
PQI | 0 | 0.08 | 0.01
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 07:32 AM el 5/04/2017